## Slide 1: DHE Product Execution Forum
DMR-RS
WW25’26

## Slide 2
Platform Dashboard –WW30
DMR-RS
Color Grading Key |  |  |  | 
All Deliverables Completed | On Track w/ No Issues | On Track w/ Approved Mitigation Plan | Platform at Risk Mitigation Plan WIP | Critical Issue(s) w/ NO Mitigation Plan
Done | On Track | On Track | At Risk | Blocked
Done | G | Y | O | R
No Help Needed | No Help Needed | No Help Needed | Might Need Help | Help Needed!!
Executive Summary.
The WW30 status is not showing broad engineering concerns; risk is concentrated in manufacturing deployment/material recovery, socket-stack qualification, and thermal model/data closure. Hardware Engineering and most DCCE domains provide a stable execution base, while Manufacturing Engineering and TME require active management attention.
The highest-priority leadership focus should be on preventing near-term schedule slips from material shortages and qualification timing: Alpha delivery exposure from the PDB resistor shortage, MDP tight-timeline recovery, Lotes socket reliability/TCT closure, and Thermals WW30 LIRA assumptions are the most visible execution-sensitive items.
Pre-PO
Entry
PRQ - PV
ERB TO
POB TO
EC
Power-On
Entry
PK
Volume
Deploy Entry
Sunset
PC
Alpha
Be-Ready
Mid-Design
(0.5)
WW28 ‘27
WW11‘25
WW48 ‘26
WW49 ‘27
WW14‘27
Notes: 2

## Slide 3
Data Center Component Engineering
  Overall DCCE execution is controlled, with most domains green; the main technical watch areas remain Power Integrity and Signal Integrity NUDD closure. CPU Package Development and VRs are green with no major blockers called out; VR validation shows progress through completed Renesas second-source activity, 900W SKU approval with no BRD/VR config change required, and ongoing Intel blue sheet work for Joulwatt telemetry/security review.
  The key WW30 challenge is residual validation confidence rather than execution breakdown: Signal Integrity remains yellow on NUDDs due to UCIe needing more electrical validation, while Power Integrity remains yellow on NUDDs because UCC1 VCCANA / IMH2 Vmin excursion risk and VR telemetry fault-injection verification still require closure; VCCIN characterization is ongoing with closure targeted for WW31 and no ES2/LIRA WW31 risk currently anticipated
Manufacturing Engineering
Manufacturing Engineering carries the highest WW30 execution exposure, with orange status in System Deployment and multiple yellow schedule/material signals across RP operations, MDP, Memory, and IHV supply. System Deployment is orange because Alpha demand is only 65% complete, with 420 units pending from a 1,200-unit Q2’26 commitment, and PDB resistor shortages are expected to stop deliveries starting WW31 with no supplier commitment yet.
Progress is visible, but recovery is dependency-heavy: RP Manufacturing reports PPV builds/shipments on track and ~65% EPS Alpha demand shipped, MDP1 has mitigated WW29 delivery risk through 16 MDP shipments using 2025-version Lotes sockets, and MDP2 remains on track but under tight-timeline monitoring; however, resistor supply, MDP cable/FRU recovery, supplier responsiveness, memory supplier pushes, and OOC/IHV quote/ETA instability remain the main leadership watch items.
Hardware Engineering
Hardware Engineering is stable in WW30, with RP HPM/PPV and System Boards green across the current dashboard. The organization is operating mainly in sustaining, regression closure, CCB evaluation, customer support, and future configuration enablement rather than active program recovery; no major schedule, NUDD, quality, or technical execution blockers are indicated in the WW30 status.
The main Hardware Engineering work is tactical closure and readiness for forward programs: RP HPM/PPV is working with Aivres to close remaining regressions despite Aivres resource delays, evaluating COR-16CH 8S support and AST2700 DCSCM intercepts, while System Boards has resolved the I2C/I3C CEM riser issue and is preparing publication instructions as Aivres continues regression documentation.
Thermal and Mechanical Engineering
TME remains a major WW30 risk area, driven by Socket Stack schedule/resource/quality/NUDD yellow status and Thermals schedule/NUDD/technical execution yellow status. Socket Stack has zero-week schedule margin to QS-16wk, Lotes socket is lagging due to changes needed to resolve TCT marginality, and long-term reliability findings persist across socket suppliers.
TME also shows meaningful mitigation progress, but not enough to remove risk: TE and FIT sockets were recommended to Google for DVT builds and Google is now ungated, LM component testing is 99% complete with final design review targeted by end of August, and cost-reduction work achieved nearly 50% reduction on PEEK ESD101 carriers; however, costs remain ~2.2x target, Lotes post-TCT failures are driving socket body changes, TE post-TCT findings remain under disposition, and Thermals still depends on PTP post-silicon data review and agreement on model assumptions during the WW30 LIRA cycle.
Cloud Systems
Cloud Systems improved to mostly green in WW30, with the remaining issue concentrated in technical execution rather than schedule or resourcing. EVT is reported as WIP and on track; after silicon pushout, DVT/Fab2 is trending Dec/January’27 and Fab3 May/June’27, while eSPI is now functional after the Intel BKC Advisory WW10 implementation and new HPM CPLD code.
The primary Cloud watchout is validation execution continuity: EVT execution is 16% complete with execution paused because ODM is moving validation activities to Malaysia, with resumption expected by August 10; NUDDs remain tied to architectural differentiators including dual-node BMC, flashless boot, third-party FPGA solution, aggregator board FPGA removal, and 48V/12V input accommodation.